## Sheet1
No. | User Stories | Acceptance Criteria | Story Points
US_06 | As a player, I want the player and AI characters to use pixel art sprites so that the characters match the retro visual style. | Player character uses a pixel art sprite. AI opponent uses a pixel art sprite. Sprites replace any placeholder shapes for characters and display correctly during gameplay. | 3
No. | Test Case Title | Test Flow | Expected Result | Points Breakdown | Execution Status
TC_06_01 | Player Character Uses Pixel Art Sprite | Launch the game and start a match. Observe the player character displayed on screen. | The player character appears as a pixel art sprite instead of a placeholder shape. | 1 | COMPLETE
TC_06_02 | AI Character Uses Pixel Art Sprite | Launch the game and start a match against an AI opponent. Observe the AI character displayed on screen. | The AI character appears as a pixel art sprite instead of a placeholder shape. | 1 | COMPLETE
TC_06_03 | Character Sprites Display Correctly During Gameplay | Start a match and play for several seconds while observing both characters. | Both player and AI characters consistently display pixel art sprites during gameplay without graphical issues. | 1 | COMPLETE
US_10 | As a player, I want smooth transitions between game stages so that gameplay feels complete and polished. | Game transitions smoothly from main menu to difficulty selection and then to the match. Difficulty settings carry into the fight. After the match ends, the player can return to the main menu or restart the game without errors or crashes. | 4
No. | Test Case Title | Test Flow | Expected Result | Points Breakdown | Execution Status
TC_10_01 | Difficulty Selection Menu Displays | Launch the game and navigate to the mode or match setup screen. | The player is presented with options to select easy, medium, or hard difficulty. | 1 | COMPLETE
TC_10_02 | Selected Difficulty Persists Into Match | Launch the game, select any difficulty, and start a match. Observe gameplay settings. | The match runs using the selected difficulty without reverting or changing unexpectedly. | 1 | COMPLETE
TC_10_03 | Difficulty Selection Loads Correct AI | Launch the game, select difficulty, and start a match. Observe AI behavior. | The AI behaves according to easy, medium, and hard difficulty. | 2 | COMPLETE
US_11 | As a player, I want the camera to keep both fighters visible during the match so that I can clearly see the action and react to my opponent. | The camera view displays both the player and AI opponent during the fight. When fighters move across the stage, the camera adjusts its position to keep both characters visible on screen. The camera does not cut off characters at the screen edges during normal gameplay. Camera movement is smooth and does not cause abrupt jumps or disorienting transitions. | 6 (2 already earned in sprint 1)
No. | Test Case Title | Test Flow | Expected Result | Points Breakdown | Execution Status
TC_11_01 | Camera Shows Both Fighters | Start a match and observe camera positioning during gameplay. | Both fighters remain visible on screen at the same time. | 3 | COMPLETE
TC_11_02 | Camera Follows Fighter Movement | Move fighters across the stage to opposite ends. | Camera adjusts position to keep both fighters visible. | 3 | COMPLETE
US_12 | As a player, I want the game environment to use pixel art graphics so that the stage matches the retro aesthetic. | The game background uses pixel art design. Background assets load correctly during gameplay. The environment visuals are consistent with the pixel art style and no placeholder backgrounds appear in the Sprint demo. | 3
No. | Test Case Title | Test Flow | Expected Result | Points Breakdown | Execution Status
TC_12_01 | Pixel Art Background Loads in Match | Launch the game and start a match. Observe the stage background when gameplay begins. | The background environment loads successfully and displays pixel art graphics. | 1 | COMPLETE
TC_12_02 | Environment Matches Pixel Art Style | Start a match and observe the environment and background elements during gameplay. | All environment visuals are designed in pixel art style consistent with the game’s retro theme. | 1 | COMPLETE
TC_12_03 | No Placeholder Background Appears | Start the demo and enter gameplay. Observe the background environment during the match. | No placeholder or unfinished background graphics appear. | 1 | COMPLETE
US_13 | As a player, I want character sprites to animate during movement and attacks so that the game feels dynamic and visually engaging. | Player sprites animate during movement and attacks. AI sprites animate during movement or attacks. Animations display smoothly during gameplay. | 8
No. | Test Case Title | Test Flow | Expected Result | Execution Status | Exectution Date
TC_13_01 | Player Sprite Animates During Movement | Start a match and move the player character left or right across the stage. | The player sprite animates correctly while moving. | 3 | COMPLETE
TC_13_02 | Player Sprite Animates During Attack | Start a match and perform an attack action with the player character. | The player sprite displays the correct attack animation when the action occurs. | 3 | COMPLETE
TC_13_03 | AI Sprite Animates During Gameplay | Start a match and observe the AI opponent moving or attacking during gameplay. | The AI character sprite animates correctly during movement or attack actions. | 2 | COMPLETE
US_17 | As a player, I want to be able to use multiple control methods such as a gamepad controller or keyboard and mouse so that I can play the game using my preferred input device. | The game accepts input from a keyboard and mouse. The game accepts input from a gamepad controller. Core gameplay actions such as movement, jumping, attacking, and blocking can be performed using either control method. The game responds correctly to inputs from either device during gameplay. | 5
No. | Test Case Title | Test Flow | Expected Result | Points Breakdown | Execution Status
TC_17_01 | Keyboard and Mouse Controls Work | Launch the game and start a match. Use the keyboard and mouse to perform actions such as movement, jumping, attacking, and blocking. | The player character responds correctly to all keyboard and mouse inputs. | 1 | COMPLETE
TC_17_02 | Gamepad Controller Controls Work | Launch the game with a connected gamepad controller and start a match. Use the controller to perform actions such as movement, jumping, attacking, and blocking. | The player character responds correctly to all controller inputs. | 2 | INCOMPLETE
TC_17_03 | Game Responds to Active Input Device | Launch the game with both a controller and keyboard connected. Start a match and perform actions using each input device. | The game correctly registers inputs from either the keyboard and mouse or the controller during gameplay. | 2 | INCOMPLETE
US_18 | As a player, I want sound effects and music in the game so that combat and menus feel more immersive and engaging. | Combat actions play sound effects during gameplay. Background music plays during menus or matches. UI interactions such as button selection and menu navigation play sound effects. Audio plays correctly without distortion or missing files. | 10
No. | Test Case Title | Test Flow | Expected Result | Points Breakdown | Execution Status
TC_18_01 | Combat Sound Effects Play | Perform attacks during gameplay. | Combat actions produce sound effects correctly. | 5 | COMPLETE
TC_18_02 | Background Music Plays | Launch the game and enter menus or matches. | Background music plays correctly during gameplay and menus. | 2 | COMPLETE
TC_18_03 | UI Sound Effects Play | Navigate menus and select buttons. | UI interactions produce sound effects correctly. | 3 | COMPLETE
US_19 | As a player, I want improved UI visuals, a settings page with volume controls, and credits so that the game feels polished and customizable. | UI art assets display correctly throughout menus and gameplay. Settings page allows the player to adjust volume levels. Volume settings affect game audio appropriately. Credits page displays team or project information correctly. | 7
No. | Test Case Title | Test Flow | Expected Result | Points Breakdown | Execution Status
TC_19_01 | UI Art Displays Correctly | Launch the game and navigate menus. | UI art assets display properly without errors. | 2 | COMPLETE
TC_19_02 | Volume Control Adjusts Audio | Open settings and modify volume controls. | Audio volume changes correctly according to settings. | 3 | COMPLETE
TC_19_03 | Credits Display Correctly | Open the credits page from the main menu. | Credits information displays correctly. | 2 | COMPLETE
US_20 | As a player, I want additional combat actions such as duck, kick, and grab so that combat gameplay has more variety and strategy. | Player can perform a duck action using a designated input. Player can perform a kick attack during gameplay. Player can perform a grab action against opponents. New actions display proper animations and function during combat. | 9
No. | Test Case Title | Test Flow | Expected Result | Points Breakdown | Execution Status
TC_20_01 | Duck Action Functions | Use the duck input during gameplay. | Player performs duck action successfully. | 2 | COMPLETE
TC_20_02 | Kick Action Functions | Use the kick input during gameplay. | Player performs kick attack successfully. | 2 | COMPLETE
TC_20_03 | Grab Action Functions | Move near an opponent and activate grab input. | Player performs grab action successfully. | 5 | INCOMPLETE
US_21 | As a player, I want the game to function without major bugs so that gameplay remains stable and enjoyable. | AI opponents perform intended combat actions during gameplay. Hard AI scoring and reward systems function correctly. Gameplay systems operate without crashes or game-breaking issues. Core mechanics work consistently during matches. | 7
No. | Test Case Title | Test Flow | Expected Result | Points Breakdown | Execution Status
TC_21_01 | Medium AI Performs Combat Actions | Start a match against medium AI and observe gameplay. | Medium AI performs intended combat actions correctly. | 2 | COMPLETE
TC_21_02 | Hard AI Uses Accurate Point System | Start a match against hard AI and observe scoring behavior. | Hard AI scoring and reward systems function correctly. | 5 | COMPLETE