## Sheet1
No. | User Stories | Acceptance Criteria | Feature | Story Points | Priority | Sprint | Team Member
US_3 | As a player, I want to be able to challenge an easy AI opponent so that I can practice basic gameplay mechanics. | An EasyController script is implemented and assigned to the AI. The AI selects actions such as block, jump, move, or attack at random. The AI moves in the general direction of the player. The AI has a slower reaction update time, making its behavior less responsive and easier to predict. | Gameplay | 10 | 1 | 2 | Inna
US_4 | As a player, I want to be able to challenge a medium AI opponent so that I can experience a balanced level of difficulty. | A MediumController script is implemented and assigned to the AI. The AI selects actions such as block, jump, move, or attack with more consistency than random behavior. The AI moves toward the player more effectively than the easy AI. The AI has a moderate reaction update time, making it more responsive than easy but not overly difficult. | Gameplay | 10 | 1 | 2 | Shariah / Gabrielle
US_5 | As a player, I want to be able to challenge a hard AI opponent so that I can face a highly challenging and intelligent opponent. | A HardController script is implemented using machine learning techniques. Unity ML-Agents are installed and configured with a working Python environment. The AI overrides CollectObservations, OnActionReceived, and OnEpisodeBegin methods. A reward and penalty system is implemented to guide AI learning. The AI is trained using a Python training process. The resulting trained neural network model is imported and used in the game. The hard AI demonstrates advanced and responsive behavior compared to easy and medium difficulties. | Gameplay | 15 | 1 | 2 | Johnny
US_11 | As a player, I want the camera to keep both fighters visible during the match so that I can clearly see the action and react to my opponent. | The camera view displays both the player and AI opponent during the fight. When fighters move across the stage, the camera adjusts its position to keep both characters visible on screen. The camera does not cut off characters at the screen edges during normal gameplay. Camera movement is smooth and does not cause abrupt jumps or disorienting transitions. | Camera System | 6 (2 already earned in sprint 1) | 3 | 2 | Anthony
US_14 | As a player, I want to be able to select between multiple difficulties so that I can choose a gameplay experience that matches my skill level. | The game provides an option to select between easy, medium, and hard difficulties before starting a match. The selected difficulty correctly loads the corresponding AI controller. The selection is clearly visible to the player. The game starts with the chosen difficulty applied. | Gameplay | 4 | 3 | 2 | Gabrielle