## UserStoriesSprint1
No. | User Stories | Acceptance Criteria | Feature | Story Points | Priority | Sprint | Team Member
US_1 | As a player, I want to access a main menu so that I can make choices in the game. | Main menu displays on game launch. Menu includes: Start, Settings, Quit, Credits. User can navigate menu using mouse. Selecting Start transitions to fight screen. Selecting Exit closes the game | Game Navigation | 5 | 1 | 1 | Gabrielle
US_7 | As a player, I want to see a health bar during the fight so that I can track progress. | Player health bar is visible on screen during the match. AI health bar is also visible. Health bars decrease when damage is taken. Health bars update in real time during combat. | Combat UI | 5 | 2 | 1 | Shariah
US_8 | As a player, I want to win or lose based on health depletion so that the fight has a clear outcome. | When the AI’s health reaches zero, the player wins. When the player’s health reaches zero, the player loses. The match ends immediately when one health bar reaches zero. No further movement or attacks occur after the match ends. | Combat System | 5 | 1 | 1 | Johnny
US_9 | As a player, I want to see a win or lose screen so that I know the match outcome. | A win screen displays when the player wins. A lose screen displays when the player loses. End screen includes options to return to the main menu or play again. Selecting an option transitions properly without crashing the game. | Game Navigation | 3 | 2 | 1 | Gabrielle
US_11 | As a player, I want the camera to keep both fighters visible during the match so that I can clearly see the action and react to my opponent. | The camera view displays both the player and AI opponent during the fight. When fighters move across the stage, the camera adjusts its position to keep both characters visible on screen. The camera does not cut off characters at the screen edges during normal gameplay. Camera movement is smooth and does not cause abrupt jumps or disorienting transitions. | Camera System | 8 | 2 | 1 | Shariah
US_14 | As a player, I want the ability to block attacks so that I can defend myself against enemy attacks during combat. | The player can activate a block action using a designated input. When blocking, incoming attacks deal reduced or no damage. A blocking animation or visual indicator appears while the player is blocking. Blocking only works while the block input is active. | Gameplay | 3 | 3 | 1 | Johnny
US_15 | As a player, I want the game to prevent my character from falling out of the environment so that gameplay stays within the intended boundaries. | The player character cannot move beyond the stage boundaries. The player cannot fall through the ground or platforms. Collision detection prevents the player from leaving the playable area. The player remains within the environment during gameplay. | Gameplay | 3 | 2 | 1 | Shariah
US_16 | As a player, I want the ability to perform a double jump so that I can reach higher areas and have greater mobility during gameplay. | The player can jump once from the ground and perform a second jump while in the air. The second jump can only occur after the first jump. The player cannot perform more than two jumps before landing. The double jump resets after the player lands on the ground. | Gameplay | 6 | 3 | 1 | Johnny
US_17 | As a player, I want to be able to use multiple control methods such as a gamepad controller or keyboard and mouse so that I can play the game using my preferred input device. | The game accepts input from a keyboard and mouse. The game accepts input from a gamepad controller. Core gameplay actions such as movement, jumping, attacking, and blocking can be performed using either control method. The game responds correctly to inputs from either device during gameplay. | Gameplay | 5 | 3 | 1 | Johnny